FAIRGAME INITIATIVE	Science fairs without barriers.

Family Science Night Kit

A two-hour evening event that shows families what their students have been building.

HOW TO USE:  Run this in the week before or after your school fair. Everything here assumes a school hall, one evening, and no budget beyond printing.

Why run one

Families support what they understand. An evening where students explain their own work turns a school requirement into something a family is proud of, and it is the single most effective recruiting tool for next year's fair.

Six-week countdown

| WHEN | WHAT TO DO |
| --- | --- |
| 6 weeks out | Pick the date, book the space, and clear it with administration. |
| 4 weeks out | Send the save-the-date home. Ask the PTO about refreshments. |
| 3 weeks out | Recruit staff and student volunteers. Confirm table and power needs. |
| 2 weeks out | Send the invitation home with the RSVP slip. Print signage. |
| 1 week out | Confirm the layout, assign students to tables, and run a practice round in class. |
| Day of | Set up two hours early. Use the Day-of-Event Checklist for logistics. |

Evening run sheet

| TIME | WHAT HAPPENS | WHO RUNS IT |
| --- | --- | --- |
| 6:00 | Doors open, families sign in, students go to their tables | Front desk volunteer |
| 6:10 | Welcome, five minutes, what a science fair is and why we do it | Coordinating teacher |
| 6:20 | Open gallery walk, families visit tables and students explain projects | All students |
| 7:10 | Three student spotlight talks, three minutes each | Selected students |
| 7:30 | Hands-on station rotation for younger siblings | Volunteers |
| 7:50 | Thank you, next steps, and how families can help | Coordinating teacher |
| 8:00 | Close and pack down | All |

Hands-on stations for younger siblings

Three low-cost stations keep younger children busy so parents can talk to their student. Each needs one volunteer.

- Sink or float: a tub of water and a basket of household objects. Children predict before testing.

- Ramp races: a board, some books, and toy cars. Change the ramp height and time the run.

- Mystery bag: sealed bags with objects inside. Children describe using touch alone, then guess.

Student table script

Print one per student. Practise it in class the week before.

My name is ____ and my project asks ____.

I chose it because ____.

Here is what I did: I changed ____ and I measured ____.

Here is what I found: ____.

The part that surprised me was ____.

COACH STUDENTS ON THIS  Families will ask did you win. Teach students to answer with what they found out instead. It shifts the evening away from competition and toward the work.

Invitation to send home

Copy onto school letterhead.

Dear Families,

Your student has spent this term designing and running their own scientific investigation. On [date] from [time] to [time] in the [location], they will present that work to you.

Come and let your student walk you through what they did. Ask them why they chose their question, what surprised them, and what they would do differently. There will be hands-on activities for younger children and refreshments for everyone.

No cost, no preparation needed, and every family is welcome. Please return the slip below by [date] so we know how many to expect.

- - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - -

Student name:  ______________________________________

Number of people attending:  ________________

Family member name:  __________________________________

Setup checklist

☐  One table per student, numbered and matched to a floor map

☐  Sign-in table with a roster and name tags

☐  Signage at the entrance, at each section, and toward the refreshments

☐  Power and extension leads for any project needing them

☐  Refreshments table set away from the project tables

☐  Camera assigned to one volunteer, photo consent checked

☐  A quiet corner for students who need a break from the crowd