## 12-Month Timeline
FAIRGAME INITIATIVE ¦ 12-MONTH FAIR TIMELINE CHECKLIST
Assumes your fair happens in month twelve. Adjust the start date to your school calendar. Mark Done as you go; pin a copy in your committee workroom.
Phase | Task | Owner (role) | Target date | Done?
Months 1-2 ¦ Approval and setup | Submit the administrator proposal | Fair Coordinator
| Form your committee of three to five people | Fair Coordinator
| Set the fair date | Fair Coordinator
| Notify your affiliate fair and register intent | Fair Coordinator
| Contact FairGame for your free setup consultation | Fair Coordinator
Months 3-4 ¦ Planning | Choose your fair format (school-only, district, multi-school, or virtual) | Committee
| Reserve the venue and confirm date with administration | Logistics Lead
| Draft the budget with the Budget Worksheet | Fair Coordinator
| Begin sponsor outreach with the sponsorship letter | Communications
Months 5-6 ¦ Recruitment | Send the judge invitation email to local professionals | Judge Coordinator
| Register with ProjectBoard and confirm safety documentation | Fair Coordinator
| Announce the fair to students and families | Communications
| Collect signed permission slips | Communications
Months 7-9 ¦ Student support phase | Hold topic selection workshops | Student Support Lead
| Check on project progress each month | Student Support Lead
| Confirm judge roster and send training materials | Judge Coordinator
Months 10-11 ¦ Final prep | Finalize judge assignments and rubric packets | Judge Coordinator
| Order trophies, ribbons, and signage | Logistics Lead
| Confirm venue logistics: tables, power, accessibility | Logistics Lead
| Send parent communication with fair-day details | Communications
Month 12 ¦ Fair and follow-up | Run fair day with the Day-of-Event Checklist | Whole committee
| Hold the awards ceremony and record advancing students | Fair Coordinator
| Send the post-event survey within one week | Communications
| Hold a committee debrief and write down changes for next year | Fair Coordinator