FAIRGAME INITIATIVE	Science fairs without barriers.

Science Fair Committee Job Descriptions

HOW TO USE:  Paste any role description into a staff recruitment email. Smaller schools can combine roles; one person may wear two hats in the first year.

A committee of three to five people splits the work into manageable pieces so no single teacher carries it all. Divide ownership early so planning does not stall when one person gets busy.

| ROLE | RESPONSIBILITY | TIME (ACTIVE PHASE) |
| --- | --- | --- |
| Fair Coordinator | Overall lead, usually the proposing teacher. Owns the timeline and communicates with the affiliate fair and with FairGame. | 5 to 8 hours per month |
| Judge Coordinator | Recruits and manages judges. Sends judges their training materials and assignments. | 2 to 3 hours per month |
| Student Support Lead | Runs workshop sessions and answers student questions as projects develop. | 2 to 3 hours per month |
| Logistics Lead | Manages the venue, tables, signage, and check-in on the day. | 2 to 3 hours per month |
| Communications | Sends parent letters, promotes the fair, and posts updates for the school community. | 2 to 3 hours per month |

TIME COMMITMENT

Plan for about 5 to 8 hours per month for the coordinator and 2 to 3 hours per month for other members during the active phase, months 7 through 12 of the timeline. FairGame support reduces this load noticeably.

RECRUITING TIP

Recruit your committee in the same week you get administrator approval, while interest is high. A short staff email that names the five roles and their hours lets colleagues pick the piece that fits their schedule.