## 8-Week Plan
FAIRGAME INITIATIVE ¦ 8-WEEK PROJECT CALENDAR
A compressed schedule for students starting later in the term. Enter your own dates in column D and check off each week. Data collection sits in weeks 5 and 6, so any project needing long observation should start those trials in week 4.
Week | Focus | What I do this week | My target date | Done?
1 | Topic and question | Choose your topic and narrow it to one testable question. Start your science journal.
2 | Background research | Read two or three credible sources. Complete a Source Summary Sheet for each.
3 | Hypothesis and design | Write your if, then, because hypothesis. Identify all three variable types and draft your procedure.
4 | Approval and materials | Get design and safety approval. Gather every material on your shopping list.
5 | Data collection | Run your trials. Record every one in your journal on the day it happens.
6 | Data collection and analysis | Finish the trials. Calculate averages and build your graph.
7 | Conclusion and board | Write your CER conclusion and your report. Build your display board.
8 | Practice and present | Write your abstract. Practice out loud until you no longer need notes.
REMEMBER
Start earlier than you think you need to. The students who do best give themselves room for trials that fail and experiments that take longer than planned. If your project needs time-based observation such as plant growth or fermentation, begin data collection in the first third of your calendar.

## 12-Week Plan
FAIRGAME INITIATIVE ¦ 12-WEEK PROJECT CALENDAR
The standard schedule, matching the FairGame curriculum. Enter your own dates in column D and check off each week as you finish it. Journal check weeks are marked so you can plan around them.
Week | Focus | What I do this week | My target date | Done?
1 | Topic exploration | Brainstorm freely. Identify a real-world problem your project connects to. Start your journal.
2 | Testable question | Narrow your topic to a question you can answer with an experiment you can actually run.
3 | Background research | Read two or three credible sources. Complete a Source Summary Sheet for each. Journal check 1.
4 | Hypothesis | Write your if, then, because hypothesis. Peer review it with a partner.
5 | Experimental design | Identify your variables and control group. Write your procedure with at least eight steps.
6 | Materials and approval | Complete your shopping list and safety check. Get teacher approval. Journal check 2.
7 | Data collection | Begin trials. Record each one the day it happens.
8 | Data collection | Continue trials. Note anything unexpected.
9 | Data collection | Finish trials. Confirm you have at least three per condition. Journal check 3.
10 | Data analysis | Calculate averages and range. Build your graph. Write your pattern description.
11 | Conclusion and report | Write your CER conclusion. Draft the full research report.
12 | Board and presentation | Build your board, write your abstract, and practice presenting. Journal check 4.
REMEMBER
Start earlier than you think you need to. The students who do best give themselves room for trials that fail and experiments that take longer than planned. If your project needs time-based observation such as plant growth or fermentation, begin data collection in the first third of your calendar.