## My Timeline
FAIRGAME INITIATIVE ¦ STUDENT PROJECT TIMELINE CHECKLIST
Adjust the dates to fit your own fair, then check off each milestone. Start earlier than you think you need to: early starts turn into calm finishes.
When | Milestone | My target date | Done?
6 months before | Choose your topic
5 months before | Complete background research
4 months before | Write your hypothesis and design your experiment
3 months before | Get approvals, if your project needs them
2 to 3 months before | Conduct your experiment
1 month before | Analyze your data and draw conclusions
3 weeks before | Create your display board
2 weeks before | Write your research paper
1 week before | Practice your presentation
Day of the fair | Arrive early and be confident